## backlog
Priority | Requirement | Assigned To | Estimate | Actual | Entered Date | Start Date | End Date | % Done | Status
1 | Load R003 Lattice and Racks | VV | 2 | 2 |  |  |  | 100
2 | Merge new version from ESS | VV | 3 | 2 |  |  |  | 100
3 | Deploy CM into production | VV | 3 | 5 |  |  |  | 100
4 | Install & Configure RBAC | VV | 5 | 7 |  |  |  | 100
5 | Install & Configure New Config Manager | VV | 10 | 8 |  |  |  | 100
6 | Migrate CM to Glassfish and MySQL | VV | 10 | 16 |  |  |  | 100
7 | Develop new Device Tree page (with assemblies) | VV | 15 | 5 |  |  |  | 60
8 | Change design for assemblies | VV | 10 | 20 |  |  |  | 90
9 | Implement approval processes | VV | 15 | 0 |  |  |  | 80
10 | Implement authorization | VV | 15 | 8 |  |  |  | 60
11 | Develop new Device Type page (with hierarchies) | VV | 10 | 5 |  |  |  | 60
12 | Design changes for device change history | VV | 2 | 1 |  |  |  | 100
13 | Develop Reports pages | VV | 10 | 0 |  |  |  | 10
14 | Make GUI changes (responsive) | VV | 10 | 3 |  |  |  | 80
15 | Develop user-based views | VV | 10 | 0 |  |  |  | 0
16 | Develop admin pages | VV | 3 | 0 |  |  |  | 10
17 | Integrate with eTraveler |  | 5 | 0 |  |  |  | 0
18 | Develop Rack Layout | VV | 8 | 0 |  |  |  | 90
19 | Generic Reports | ESS
20 | Enhance API | VV | 10 | 0 |  |  |  | 10
21 | Bug Fixes | ESS
22 | Update data loaders | ESS | 10 | 0
23 | Data Loading | VV | 40 | 5 |  |  |  | 20
24 | Design changes for device ports | VV | 2 | 2 |  |  |  | 100
25 | Add channels to devices | VV | 3 | 0 |  |  |  | 0
26 | Integrate with Calibration |  | 3 | 0 |  |  |  | 0
27 | Integrate with Cables |  | 5 | 0 |  |  |  | 0
28 | Integrate with Naming |  | 5 | 0 |  |  |  | 0
29 | Develop high level requirements | VV | 10 | 5 |  |  |  | 30
30 | Integrate RBAC with CM | ESS | 5 | 0 |  |  |  | 0
31 | EPICS interface |  | 5 | 0 |  |  |  | 0
32 | Migrate RBAC to Glassfish and MySQL |  | 10 | 0 |  |  |  | 0
33 | Interface with RPS |  | ? |  |  |  |  | 0
| Totals |  | 254 | 94

## sprints
Sprint | Name | Start date | Priority | Description
1 | Feb-I | 2016-02-01
|  |  | 1 | Develop new Device Tree page (with assemblies)
|  |  | 2 | Develop new Device Type page (with hierarchies)
2 | Feb-II | 2016-02-15
|  |  | 1 | Develop Reports pages
|  |  | 2 | Implement approval processes
|  |  | 3 | Make GUI changes (responsive)
3 | Mar-I | 2016-03-01
|  |  | 1 | Develop user-based views
|  |  | 2 | Refactor (Enhance Feb-I and Feb-II tasks)
4 | Mar-II | 2016-03-14
|  |  | 1 | Enhance API
|  |  | 2 | Refactor (Enhance Feb-I and Feb-II tasks)
5 | Apr-I | 2016-04-04
|  |  | 1 | Integration with lattice, traveler, cabls, naming, calibration
6 | Apr-II | 2016-04-18
|  |  | 1 | Integration with lattice, traveler, cabls, naming, calibration

## deadlines
# | Date | Tasks | Comments
1 | Jan 2015 – Feb 2016 | HV Platform Utilities
2 | 2016-02-01 | Racks, Artemis
3 | Feb-Mar 2016 | Trays, Stands, RFQ Amp
4 | March 16-17 | ESHAC Review | ion source needs to be as well populated as possible, since that will be the first ARR,
5 | Apr-Jun 2016 | LEBT Components, Populate Racks
6 | 2016-05-01 | Vertical Beam Line
7 | 2016-07-01 | RFQ In Tunnel (start conditioning
8 | Jul-Sept 2016 | LEBT/MEBT In Tunnel